## Procurement Plan
Inter-American Development Bank
IFD/CTI
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Belize, Guyana, Jamaica and Trinidad and Tobago |  |  |  |  | Executing agency: The University of the West Indies |  |  |  |  | Public or private sector: Public
Project number: RG-T4186 |  |  |  |  | Title of Project: CaribData: Caribbean Data-Driven Resilience
Period covered by the plan: : December 2022- December 2025
Threshold for ex-post review of procurements: 2 months |  |  |  | Goods and services (in US$): |  | 40000 |  | Consulting services(in US$): | 480000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
1 | 90000 | Component 1: Data Infrastructure and Roadmap for Data Resiliency | [8 empty] | International Competitive Bidding
National Competitive Bidding
|  | Firm consulting services | [8 empty] | Individual Consultant
|  | Implementation of Data Sharing Infrastructure Tool | 90000 | QCBS | Ex-ante | 100% |  | 2024-02-01 | Yes |  | National System
Individual consultant
|  | Front-end support | 50000 | SSS | Ex-ante | 100% |  | 2023-10-01 | Yes
2 | 175000 | Component 2: Data Analytics Training and Knowledge Generation | [8 empty] | International Competitive Bidding
National Competitive Bidding
|  | Firm consulting services | [8 empty] | Individual Consultant
|  | Data Science Training, Datathons, Data Communication, Sustainability | 150000 | CQS | Ex-ante | 100% |  | 2024-02-01 | Yes |  | National System
Non-consulting services
|  | Editing Services | 15000 | DC | Ex-ante | 100% |  | 2023-10-01 | Yes
|  | Regional Data Sharing Conference | 10000 | DC | Ex-ante | 100% |  | 2025-01-01 | Yes
3 | 120000 | Component 3: Data Audits, Guidelines and Policies | [8 empty] | International Competitive Bidding
National Competitive Bidding
|  | Individual consultants | [8 empty] | Individual Consultant
|  | Data Audit and Data Processing Analyst | 120000 | IICQ | Ex-ante | 100% |  | 2023-10-01 | Yes
4 | 85000 | Component 4: Project Coordination, Communication, and Evaluation | [8 empty] | Ex Post
Individual consultants
|  | Project Assistant | 50000 | IICQ | Ex-ante | 100% |  | 2024-01-01 | Yes
|  | Final Evaluation | 20000 | IICQ | Ex-ante | 100% |  | 2025-08-01 | Yes
Non-consulting services
|  | Public Awareness Campaign and Marketing Activities | 5000 | PC | Ex-ante | 100% |  | 2025-03-01 | Yes
|  | Auditing | 10000 | CB | Ex-ante | 100% |  | 2025-08-01 | Yes
Total |  |  | 520000 | Prepared by: Team Leader |  |  | Date: September 06, 2023
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.